## Sheet1
Test Case ID | Description | Priority | QA | Testing Status | Developers Status
navExpoloader | Navigate the URL |  | Zabith | Tested | Developed
signupExpo | Test Different combination of Username value. Eg: Empty username,Empty password,Empty Email, Valid Username, Invalid Username,Invalid Email,invalid password, valid password, Empty Check Box |  | Suresh | Tested | Developed
loginExpo | Test Different combination of Username Eg: Empty username,Empty password, Valid Username, Invalid Username,Invalid Password,valid password |  | Suresh | Tested | Developed
expoSKUAddNew | Test SKU management in Expoloader. AddNew |  | Amna | Tested | Developed
expoSKUIExportExcel | Test SKU management in Expoloader exportExel |  | Amna | Tested | Developed
expoSKUEdit | Test SKU management in Expoloader edit |  | Amna | Tested | Developed
expoSKUDelete | Test SKU management in Expoloader delete. |  | Zabith | Tested | Developed
expoSKUSearch | Test SKU management in Expoloader Search |  | Zabith | Tested | Developed
expoSKUDeleteAllRecords | Test SKU management in Expoloader DeleteAllRecords |  | Zabith | Tested | Developed
expoSKUImportExcelData | SKU import excel data |  | Zabith | Tested | Developed
expoContainerAddNew | Test Container management in Expoloader AddNew |  | Thilina/thisun | Tested | Developed
expoContainerExportExcel | Test Container management in Expoloader ImportExel |  | Thilina | Tested | Developed
expoContainerEdit | Test Container management in Expoloader edit |  | Thilina | Tested | Developed
expoContainerDelete | Test Container management in Expoloader delete. |  | Tisun | Tested | Developed
expoContainerSearch | Test Containermanagement in Expoloader Search |  | Tisun | Tested | Developed
expoContainerDeleteAllRecords | Test Containermanagement in Expoloader DeleteAllRecords |  | Tisun | Tested | Developed
expoContainerImportExcelData | container import excel data |  | Zabith | Tested | Developed
expoPalleteAddNew | Test Pallete management in Expoloader. AddNew |  | Zabith | Tested | Developed
expoPalleteImportExcel | Test Pallete management in Expoloader ImportExel |  | Zabith | Tested | Developed
expoPalleteEdit | Test Palletemanagement in Expoloader edit |  | Zabith | Tested | Developed
expoPalleteDelete | Test Palletemanagement in Expoloader delete. |  | Zabith | Tested | Developed
expoPalleteSearch | Test Pallete management in Expoloader Search |  | Zabith | Tested | Developed
expoPalleteDeleteAllRecords | Test Palletemanagement in Expoloader DeleteAllRecords |  | Zabith | Tested | Developed
expoPalleteExportExcel | pallet export excel data |  | Zabith | Tested | Developed
floorLoading | Test basic container loading ex-Add LoadingType,Container,Height,SKU |  | Amna | Tested | Developed
palletLoading | Test basic container loading ex-Add LoadingType,Container,Height,SKU |  | Amna | Tested | Developed
floorAndPalletLoading | test floor and pallet loading in the optimization |  | Ayesh | Tested | Developed
multiSkuFloorLoading | Test multiple sku |  | Zabith | Tested | Developed
palletStackMultiSkuLoad | Test multiple sku |  | Ayesh | Tested | Developed
palletNonStackMultiSkuLoad | Test multiple sku |  | Ayesh | Tested | Developed
logOut | Logout of the website |  | Ayesh | Tested | Developed
email Verification | Check signup Emial verification |  | Zabith | Tested | Developed
notificationContainerAddNew | Test notifications in expoloader website |  | Thilina/ayesh/thisun/suresh | Pending | Developed
notificationContainerDelete | Test notifications in expoloader website |  | Thilina/ayesh/thisun/suresh | Pending | Developed
notificationContainerDeleteAllRecord | Test notifications in expoloader website |  | Thilina/ayesh/thisun/suresh | Pending | Developed
notificationContainerEdit | Test notifications in expoloader website |  | Thilina/ayesh/thisun/suresh | Pending | Developed
notificationPalletAddNew | Test notifications in expoloader website |  | Thilina/ayesh/thisun/suresh | Pending | Developed
notificationPalletDelete | Test notifications in expoloader website |  | Thilina/ayesh/thisun/suresh | Pending | Developed
notificationPalletDeleteAllRecord | Test notifications in expoloader website |  | Thilina/ayesh/thisun/suresh | Pending | Developed
notificationPalletEdit | Test notifications in expoloader website |  | Thilina/ayesh/thisun/suresh | Pending | Developed
notificationSKUAddNew | Test notifications in expoloader website |  | Thilina/ayesh/thisun/suresh | Pending | Developed
notificationSKUDelete | Test notifications in expoloader website |  | Thilina/ayesh/thisun/suresh | Pending | Developed
notificationSKUDeleteAllRecord | Test notifications in expoloader website |  | Thilina/ayesh/thisun/suresh | Pending | Developed
notificationSKUEdit | Test notifications in expoloader website |  | Thilina/ayesh/thisun/suresh | Pending | Developed
notificationProjectsAddNew | Test notifications in expoloader website |  | Thilina/ayesh/thisun/suresh | Pending | Developed
notificationProjectsDelete | Test notifications in expoloader website |  | Thilina/ayesh/thisun/suresh | Pending | Developed
notificationProjectsDeleteAllRecord | Test notifications in expoloader website |  | Thilina/ayesh/thisun/suresh | Pending | Developed
notificationProjectsEdit | Test notifications in expoloader website |  | Thilina/ayesh/thisun/suresh | Pending | Developed
notificationConsignmentsAddNew | Test notifications in expoloader website |  | Thilina/ayesh/thisun/suresh | Pending | Developed
notificationConsignmentsDelete | Test notifications in expoloader website |  | Thilina/ayesh/thisun/suresh | Pending | Developed
notificationConsignmentsDeleteAllRecords | Test notifications in expoloader website |  | Thilina/ayesh/thisun/suresh | Pending | Developed
notificationConsignmentsDeleteEdit | Test notifications in expoloader website |  | Thilina/ayesh/thisun/suresh | Pending | Developed
notificationPersonalInfo | Test notifications in expoloader website |  | Thilina/ayesh/thisun/suresh | Pending | Developed
notificationDeleteAccount | Test notifications in expoloader website |  | Thilina/ayesh/thisun/suresh | Pending | Developed
searchProject | test project management search |  | Suresh | Tested | Developed
projectAdd | test project add |  | thisun | Tested | Developed
projectEdit | test project Edit |  | thisun | Tested | Developed
projectDelete | test project Delete |  | thisun | Tested | Developed
projectDeleteAllRecords | test project delete all records |  | thisun | Tested | Developed
projectDetailAddUser | test project details add user |  | Zabith | Tested | Developed
projectDetailEditUser | test project details Edit |  | Zabith | Tested | Developed
projectDetailsDelete | test project details Delete user |  | Zabith | Tested | Developed
consignmentSearch | test consegment management's search function |  | Ayesh | Tested | Developed
consignmentEdit | test consegment management's edit function |  | Ayesh | Tested | Developed
consignmentDelete | test consegment management's delete function |  | Navindu | Tested | Developed
consignmentDeleteAllRecords | test consegment management's DeleteAll function |  | Navindu | Tested | Developed
personalInfo | test personal Info |  | Amna | Tested | Developed
changePassword | test change password function |  | sarfan | Pending | Developed
deleteAccount | test delete account |  | sarfan | Pending | Developed
forgetPassword | test forget password |  | Zabith | Tested | Developed